# Transition Iteration 1 Plan

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Discipline | Use Case | Activities | Estimated Hours | Actual Hours | % Completed | Resources |
| Learning | Learning new technologies | Watching Pluralsight videos | 20 | 20 | 100% | Developer |
| Set up Azure site and database | Initial Configuration | Azure configuration | 5 | 5 | 100% | Lead developer |
| Set up Github repository | Initial Configuration | Github configuration | 1 | 1 | 100% | Lead developer |
| Create Data models | Initial Development | Create classes for data model | 5 | 10 | 100% | Developer |
| Set up debug connection for localdb | Initial Development | Create data connection | 1 | 1 | 100% | Developer |
| Create global layout | Initial Development | Create UI | 5 | 10 | 100% | Developer  Designer |
| Create Registration UI | Registration | Create classes and UI forms | 6 | 5 | 100% | Developer  Designer |
| Create Reservation UI | Reservation | Create classes and UI forms | 12 | 3 | 100% | Developer  Designer  DBA |
| Create Standing Reservation UI | Standing Reservation | Create classes and UI forms | 12 | 1 | 100% | Developer  Designer  DBA |
| Create Enter Score Functionality | Enter Score | Create classes and UI forms | 6 |  | 0% | Developer  Designer  DBA |
| View/Modify Score | View/Modify Score | Create classes and UI forms | 8 |  | 0% | Developer  Designer  DBA |
| Create Member Profile Functionality | View/Update Profile | Create classes and UI forms | 18 |  | 0% | Developer  Designer  DBA |
| Create Admin Login UI | Admin Login | Create classes and UI forms | 6 | 1 | 100% | Developer  Designer  DBA |
| Modify Registration UI for Admins | Admin Add Member | Modify UI | 6 | 1 | 100% | Developer  Designer |
| Create Update Reservation UI for Admins | Admin Update Reservation | Create UI forms | 6 |  | 0% | Developer  Designer |
| Modify Create Reservation UI | Admin Create Reservation | Modify UI | 6 |  | 0% | Developer  Designer |

## Transition Iteration 1 Schedule

Phase: Iteration

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Iteration | Minor Milestone | Start Date | End Date | Resources |
| 1 | Beta | March 15, 2016 | April 5, 2016 | Developer, Tester (2), Designer, DBA |